## Task List a file location
STATUS | FILENAME | FOLDER PATH | DESCRIPTION
DONE | BuildMenuUI.cs | Assets/UI | Handles the Build menu tabs and object lists.
DONE | Button.prefab | Assets/UI/Prefabs | Generic Button Prefab
DONE | CameraBoundsHelper.cs | Assets/Systems/Camera | Supporting classes for panning limits, saving look-point, gesture interpretation, inertia.
DONE | CameraController.cs | Assets/Systems/Camera | Pinch-to-zoom, two-finger pan/rotate, bounded by grid extents
DONE | CameraSaveManager.cs | Assets/Systems/Camera | Save and load Camera positioning
DONE | ChatGPTExportTool.cs | Assets/Editor | Editor utilities
DONE | ContextIconCanvas.prefab | Assets/UI/Prefabs | Ghost-placement commit/cancel buttons.
DONE | EncryptedHabitStorage.cs | Assets/Data/SaveLoad | per encryption best practices in TDD §5
DONE | FolderCreator.cs | Assets/Editor | Editor utilities
DONE | GestureInputHandler.cs | Assets/Systems/Camera | Utility to handle touch gestures
DONE | GridManager.cs | Assets/Managers | Manages grid cells, elevations, slope metadata (GridCellData, TerrainType, SlopeType)
DONE | HabitData.cs | Assets/Data/Habits | Model with HabitID, Frequency, LastCompletionDate, streak info
DONE | HabitIntegrationManager.cs | Assets/Managers | Processes manual and automated completions/failures
DONE | MomentumTracker.cs | Assets/Systems/Camera | Utility to use inertia in camera movements
DONE | ObjectManager.cs | Assets/Managers | Spawns prefabs from ParkObjectData, updates grid, deducts cost
DONE | ParkBuilder.cs | Assets/Systems/Placement | Handles ghost previews, snap logic, commit/cancel flow
DONE | ParkObjectData.cs | Assets/Data/ParkObjects | Defines cost, attraction, needs, tiers, etc.
DONE | ParkObjectDataEditor.cs | Assets/Editor | Custom inspector for ParkObjectData.
DONE | ParkTypeRules.cs | Assets/Systems | Validates placement/upgrade rules per park type
DONE | PlaceableCatalog.cs | Assets/Data/UI | Data-driven catalog for the store UI.
DONE | PlayerDataManager.cs | Assets/Managers | Manages saved player profile, habits, park state, placed objects, visitor history, achievements
DONE | SaveManager.cs | Assets/Systems/SaveLoad | Handles auto-save, explicit save, versioning for JSON/binary serializations
DONE | ZoomProfile.cs | Assets/Data/ParkObjects | drives map zoom levels per object
PARTIAL | AchievementData.cs | Assets/Data/Achievements | Models and enums for tracking and rewarding achievements
TODO | AchievementSystem.cs | Assets/Managers | Registers listeners, updates progress, fires unlock events
TODO | AchievementType.cs | Assets/Data/Achievements | Models and enums for tracking and rewarding achievements
TODO | FinanceManager.cs | Assets/Systems/Financial | Implements SimulateMonth(), calculates income/expenses, donation logic
TODO | HealthConnectManager.cs | Assets/Managers | Android plugin bridge singleton handling permissions and data fetch
TODO | IMonthlyUpdatable.cs | Assets/Systems/Financial | Interface for systems that hook into the monthly loop
TODO | MaintenanceManager.cs | Assets/Systems/Financial | Applies degradation costs per object on each month
TODO | NeedType.cs | Assets/Data/SharedEnums | Visitor Needs
PARTIAL | PlacedObject.cs | Assets/Data/SaveLoad | Data model containing ObjectID, Position, Rotation, optional custom data.
TODO | QuidProQuoSystem.cs | Assets/Systems/Financial | Tracks political grants and their requirements.
TODO | RewardType.cs | Assets/Data/Achievements | Models and enums for tracking and rewarding achievements
TODO | Visitor.cs | Assets/Models | Data model with ID, VisitorType, Needs, currentSatisfaction PlexiPark_ Technical De…
TODO | VisitorAI.cs | Assets/Systems/Visitors | FSM for wandering → need fulfillment → leaving
TODO | VisitorManager.cs | Assets/Systems/Visitors | Spawn/despawn logic, compatibility checks via VisitorCompatibilityMatrix
TODO | VisitorType.cs | Assets/Data/SharedEnums | Defines visitor and need enums

## Task Sheet
Phase | Sprint/Week | Task | Effort Est. (hrs) | Task Description
Phase 0 | Week 1-2 | Set up Unity 2023.3 project with URP preset | 2 | Development task as described in timeline.
Phase 0 | Week 1-2 | Establish folder structure: Managers, Systems, UI, Data, Plugins, Core | 2 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 0 | Week 1-2 | Write naming and folder convention guide | 2 | Development task as described in timeline.
Phase 0 | Week 1-2 | Implement base ScriptableObject: ParkObjectData | 6 | Development task as described in timeline.
Phase 0 | Week 1-2 | Initialize Git repository with .gitignore and main/dev branches | 2 | Development task as described in timeline.
Phase 0 | Week 1-2 | Set up CI pipeline (Unity Cloud Build or equivalent) | 2 | Development task as described in timeline.
Phase 0 | Week 1-2 | Integrate Unity Test Framework for PlayMode & EditMode | 4 | Development task as described in timeline.
Phase 0 | Week 1-2 | Draft system for encrypted local storage of habit data | 2 | Development task as described in timeline.
Phase 1 | Week 3 | Implement GridManager.cs | 6 | Implement logic for grid initialization, occupancy, and tile metadata.
Phase 1 | Week 3 | Implement ParkBuilder.cs | 6 | Handles object previewing, placement validation, and final placement logic.
Phase 1 | Week 3 | Implement ObjectManager.cs | 6 | Central manager for instantiating prefabs and tracking placed objects.
Phase 1 | Week 3 | Create sample ParkObjectData assets (Bench, Tree, Restroom) | 6 | Development task as described in timeline.
Phase 1 | Week 3 | Build ghost preview with snapping and commit/cancel flow | 2 | Development task as described in timeline.
Phase 1 | Week 4 | Implement PlayerDataManager.cs | 6 | Development task as described in timeline.
Phase 1 | Week 4 | Implement PlacedObject data model | 6 | Development task as described in timeline.
Phase 1 | Week 4 | Implement JSON-based save/load system | 6 | Development task as described in timeline.
Phase 1 | Week 4 | Build top bar UI (balance, date, rating) | 2 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 5 | Implement Visitor.cs and VisitorType enum | 6 | Define visitor types and core simulation logic for movement and needs.
Phase 1 | Week 5 | Implement VisitorManager.cs | 6 | Define visitor types and core simulation logic for movement and needs.
Phase 1 | Week 5 | Implement VisitorAI.cs with Wandering state | 6 | Define visitor types and core simulation logic for movement and needs.
Phase 1 | Week 5 | Add RequestPathTo stub method with linear interpolation | 2 | Development task as described in timeline.
Phase 1 | Week 5 | Create Build Menu UI shell with mock data | 6 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 5 | Create Habit Menu UI shell with mock data | 6 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 6 | Add Needs and Satisfaction to Visitor.cs | 2 | Define visitor types and core simulation logic for movement and needs.
Phase 1 | Week 6 | Implement CalculateSatisfaction() | 6 | Development task as described in timeline.
Phase 1 | Week 6 | Detect proximity to facilities (e.g., Restroom) | 2 | Development task as described in timeline.
Phase 1 | Week 6 | Implement tooltip UI for visitor info | 6 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 6 | Create debug UI panel with developer toggles | 6 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 7 | Implement FinanceManager.cs | 6 | Calculate park income and expenses based on simulation rules.
Phase 1 | Week 7 | Define IMonthlyUpdatable interface | 2 | Development task as described in timeline.
Phase 1 | Week 7 | Have systems register with SimulateMonth() loop | 2 | Development task as described in timeline.
Phase 1 | Week 7 | Add Monthly Simulation trigger to UI | 2 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 8 | Implement HabitIntegrationManager.cs | 6 | Central system for processing manual and automated habit inputs.
Phase 1 | Week 8 | Create HabitData model | 6 | Development task as described in timeline.
Phase 1 | Week 8 | Implement RealWorldCompleted() / RealWorldFailed() | 6 | Development task as described in timeline.
Phase 1 | Week 8 | Connect Habit UI to manual tracking logic | 2 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 9 | Test Visitor â†’ Facility â†’ Satisfaction â†’ Finance loop | 4 | Define visitor types and core simulation logic for movement and needs.
Phase 1 | Week 9 | Test Habit â†’ Reward â†’ Income boost logic | 4 | Development task as described in timeline.
Phase 1 | Week 9 | Test placement â†’ cost â†’ maintenance pipeline | 4 | Development task as described in timeline.
Phase 1 | Week 9 | Use debug panel for simulation and testing | 2 | Development task as described in timeline.
Phase 1 | Week 10 | Add Title Screen and Park Selection stub | 2 | Development task as described in timeline.
Phase 1 | Week 10 | Finalize prefab visuals and data bindings | 3 | Development task as described in timeline.
Phase 1 | Week 10 | Polish UI transitions and responsiveness | 3 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 1 | Week 10 | Document current code state and known issues | 3 | Development task as described in timeline.
Health Connect | Week 3-4 | Create Android Studio project for .aar plugin | 6 | Development task as described in timeline.
Health Connect | Week 3-4 | Stub PlexiParkHealthPlugin class and methods | 3 | Development task as described in timeline.
Health Connect | Week 5 | Implement HealthConnectManager.cs singleton in Unity | 6 | Native Android plugin to retrieve health metrics from Health Connect API.
Health Connect | Week 5 | Set up UnitySendMessage callback structure | 2 | Development task as described in timeline.
Health Connect | Week 6-7 | Add permission UI and status indicator in Unity | 2 | Create or enhance Unity UI for system interaction or visual feedback.
Health Connect | Week 6-7 | Implement native Android permission dialog | 6 | Development task as described in timeline.
Health Connect | Week 8-9 | Query real Health Connect data (steps, distance, floors) | 2 | Development task as described in timeline.
Health Connect | Week 8-9 | Pass HealthData JSON into Unity for parsing | 2 | Deserialize and route health data into the habit system.
Health Connect | Week 10 | Test plugin on multiple Android devices | 4 | Development task as described in timeline.
Health Connect | Week 10 | Handle all fallback and permission-denied cases | 2 | Development task as described in timeline.
Phase 2 | Week 11-20 | Implement park type constraints (Urban, Suburban, Wilderness) | 6 | Development task as described in timeline.
Phase 2 | Week 11-20 | Implement full Compatibility Matrix logic | 6 | Development task as described in timeline.
Phase 2 | Week 11-20 | Add remaining visitor types and update VisitorAI FSM | 2 | Define visitor types and core simulation logic for movement and needs.
Phase 2 | Week 11-20 | Extend SimulateMonth() to support new income types | 2 | Development task as described in timeline.
Phase 2 | Week 11-20 | Implement Achievements system and badge UI | 6 | Create or enhance Unity UI for system interaction or visual feedback.
Phase 2 | Week 11-20 | Add facility maintenance level system | 2 | Development task as described in timeline.
Phase 2 | Week 11-20 | Expand UI with Manage, Achievements, and Visitor tabs | 2 | Define visitor types and core simulation logic for movement and needs.
Camera System
| Task ID | Task |  | Notes
Phase 1 | C1.1 | Refactor CameraController.cs into modular structure |  | Improves maintainability
Phase 1 | C1.2 | Add one-finger drag panning (touch + mouse right-drag) |  | Uses view-relative XZ translation
Phase 1 | C1.3 | Add two-finger pinch-to-zoom and mouse scroll fallback |  | Clamp min/max zoom distances
Phase 1 | C1.4 | Add two-finger rotate and mouse middle-drag fallback |  | Clamp rotation to yaw axis
Phase 1 | C1.5 | Apply 45° downward pitch to camera |  | Lock tilt to a fixed angle
Phase 2 | C2.1 | Add seamless gesture chaining (pan & zoom) |  | Use touch ID tracking
Phase 2 | C2.2 | Add two-finger vertical drag to tilt |  | Clamp to prevent extreme pitch
Phase 2 | C2.3 | Implement gesture-based momentum |  | Track velocity and apply deceleration
Phase 2 | C2.4 | Add damping/spring bounce-back when out of bounds |  | Use AnimationCurve or SmoothDamp
Phase 2 | C2.5 | Add smooth zoom interpolation |  | Use Lerp or SmoothDamp
Phase 3 | C3.1 | Add runtime clamp logic based on GridManager size |  | Use GridManager.origin + padding
Phase 3 | C3.2 | Make clamp buffer adjustable in Inspector |  | Field: panClampBuffer
Phase 3 | C3.3 | Clamp zoom & rotation via ZoomProfile |  | Expose min/max pitch and yaw
Phase 3 | C3.4 | Prevent camera from hiding behind UI |  | Use UI-safe zones
Phase 4 | C4.1 | Implement CameraState struct |  | Serializable for saving
Phase 4 | C4.2 | Save CameraState.XZ on park close |  | Keep zoom/rotation default
Phase 4 | C4.3 | Load XZ position on park load |  | Recenter camera
Phase 4 | C4.4 | Reset rotation and zoom on park load |  | Defaults from ZoomProfile or constant
Phase 5 | C5.1 | Add Snap to Center button |  | Recenters on park center
Phase 5 | C5.2 | Add double-tap to focus on object/tile |  | Uses raycast
Phase 5 | C5.3 | Add Gizmo debug sphere for pivotPoint |  | Editor-only
Phase 5 | C5.4 | Add debug HUD showing cam state |  | Toggleable in dev mode
Phase 5 | C5.5 | Add developer toggle to lock camera |  | Useful during placement
Phase 6 | C6.1 | Block gestures when dragging UI |  | Integrate with EventSystem
Phase 6 | C6.2 | Prevent camera from panning under UI |  | Use screen edge buffer
Phase 6 | C6.3 | Lock camera in modal states |  | Prevent gesture conflicts

## Sheet2
TODO
PARTIAL
DONE